## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1
3654545 | 68407 | ATM Project | 16 | ATM_1-16 | 292970 | Bug |  |  | 63929 | ATM 1.0 | Incorrect Bank Inquiry | Function being tested: Bank Inquiry Initial State of the System: System is displaying the "Account to inquire from" menu Steps to reproduce the defect: Insert a card (card 1) Enter correct PIN (pin 42) Choose transaction type (balance inquiry) Choose account to inquire from (money market) Expected Outcome: The system shows an invalid account type message, since card 1 does not have a money market account. Nothing should be dispensed or inquired. Actual outcome: The system shows "Unknown Error" and $500 pops up on the screen and is dispensed in the log. Also inquires about the incorrect account (savings account). | 1 | Open | 3 | Normal | [6 empty] | 319984 | Sadia Khan | Jan. 27, 2022 10:02 |  | 319984 | Sadia Khan | Jan. 27, 2022 10:03 | 0 | 0
3654533 | 68407 | ATM Project | 15 | ATM_1-15 | 292970 | Bug |  |  | 63929 | ATM 1.0 | Missing Types of Account to Inquire From | Function being tested: Bank Inquiry Initial State of the System: System is displaying the "Account to inquire from" menu Steps to reproduce the defect: Insert a card (card 1) Enter correct PIN (pin 42) Choose transaction type (balance inquiry) Expected Outcome: The system should show checking, savings and money market options Actual outcome: The system shows only checking and money market (missing savings option) | 1 | Open | 3 | Normal | [6 empty] | 319984 | Sadia Khan | Jan. 27, 2022 09:53 |  | 319984 | Sadia Khan | Jan. 27, 2022 09:53 | 0 | 0
3654523 | 68407 | ATM Project | 14 | ATM_1-14 | 292970 | Bug |  |  | 63929 | ATM 1.0 | Deposits Incorrect Amount | Function being tested: Depositing money to checking account Initial State of the System: System has completed a deposit transaction for a checking account Steps to reproduce the defect: Insert a card (card 1) Enter correct PIN (pin 42) Choose transaction type (deposit) Choose the account to deposit to (checking) Choose amount to deposit ($20) Click to insert envelope Expected Outcome: The total balance for the checking account is $120. Actual outcome: The total balance for the checking account is $110. | 1 | Open | 3 | Normal | [6 empty] | 319984 | Sadia Khan | Jan. 27, 2022 09:44 |  | 319984 | Sadia Khan | Jan. 27, 2022 09:44 | 0 | 0
3649746 | 68407 | ATM Project | 12 | ATM_1-12 | 292970 | Bug |  |  | 63929 | ATM 1.0 | Missing Dollar Sign in a Withdrawal Option | Function being tested: Withdrawal amounts menu Initial State of the System: System is displaying the menu of withdrawal amounts Steps to reproduce the defect: Insert a card (card 1) Enter correct PIN (pin 42) Choose transaction type (withdrawal) Choose the account to withdraw from (checking) Expected Outcome: The system should have a dollar sign in front of every withdrawal option in the menu Actual outcome: The $60 withdrawal option is missing the dollar sign | 1 | Open | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 25, 2022 22:07 |  | 319984 | Sadia Khan | Jan. 27, 2022 09:36 | 0 | 0
3654507 | 68407 | ATM Project | 13 | ATM_1-13 | 292970 | Bug |  |  | 63929 | ATM 1.0 | Withdraws Incorrect Amount | Function being tested: Withdrawal Initial State of the System: System is displaying the menu of withdrawal amounts Steps to reproduce the defect: Insert a card (card 1) Enter correct PIN (pin 42) Choose transaction type (withdrawal) Choose the account to withdraw from (checking) Select amount to withdraw ($20) Expected Outcome: The system withdraws $20 from the checking account Actual outcome: The system withdraws $40 from the checking account | 1 | Open | 3 | Normal | [6 empty] | 319984 | Sadia Khan | Jan. 27, 2022 09:32 |  | 319984 | Sadia Khan | Jan. 27, 2022 09:32 | 0 | 0
3649683 | 68407 | ATM Project | 11 | ATM_1-11 | 292970 | Bug |  |  | 63929 | ATM 1.0 | Incorrect Card Number on Receipt | Function being tested: Receipt information Initial State of the System: System has completed a withdrawal transaction Steps to reproduce the defect: Insert a card (card 1) Enter correct PIN (pin 42) Choose transaction type (withdrawal) Choose the account to withdraw from (checking) Select amount to withdraw ($20) Expected Outcome: The system outputs the correct card number on the receipt (card number should be 1) Actual outcome: The system outputs the incorrect card number on the receipt (card number 2 is shown instead of 1) | 1 | Open | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 25, 2022 21:47 |  | 319984 | Sadia Khan | Jan. 27, 2022 09:29 | 0 | 0
3646279 | 68407 | ATM Project | 7 | ATM_1-7 | 292970 | Bug |  |  | 63929 | ATM 1.0 | MFT: Balance Inquiry Bug Test 33 | Function being tested: System asks customer to choose an account to inquire about Initial State of the System: Menu of transaction types is being displayed Steps to reproduce the defect: 1. Select #4 on the keypad for Balance Inquiry Expected outcome: The ATM should give the options of Checking or Savings for Card 1 Actual outcome: The ATM gives options of Checking and Money Market | 2 | In Progress | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 24, 2022 23:32 |  | 319982 | Adam Abouelhassan | Jan. 26, 2022 21:03 | 0 | 0 | Jan. 25, 2022 21:27 Adam Abouelhassan Defect still exists in version 1.1
3649430 | 68407 | ATM Project | 10 | ATM_1-10 | 292970 | Bug |  |  | 63929 | ATM 1.0 | MFT: Invalid PIN Extension bug Test 37 | Function being tested: Correct re-entry of pin on the third try is accepted Initial State of the System: Request to re-enter PIN is being displayed Steps to reproduce the defect: 1. Enter correct PIN Expected Outcome: The ATM machine will log the user in Actual outcome: The ATM prompts the user to enter their PIN again | 2 | In Progress | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 25, 2022 20:27 |  | 319982 | Adam Abouelhassan | Jan. 25, 2022 22:03 | 0 | 0 | Jan. 25, 2022 21:17 Adam Abouelhassan Defect still exists in version 1.1
3649413 | 68407 | ATM Project | 9 | ATM_1-9 | 292970 | Bug |  |  | 63929 | ATM 1.0 | MFT: Invalid Pin Extension Bug Test 39 | Function being tested: Correct re-entry of pin on the third try is accepted Initial State of the System: Request to re-enter PIN is being displayed Steps to reproduce the defect: 1. Enter incorrect PIN 2. Enter correct PIN Expected Outcome: The ATM machine will log the user in Actual outcome: The ATM prompts the user to enter their PIN again | 2 | In Progress | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 25, 2022 20:22 |  | 319982 | Adam Abouelhassan | Jan. 25, 2022 22:03 | 0 | 0 | Jan. 25, 2022 21:18 Adam Abouelhassan Defect still exists in version 1.1
3646120 | 68407 | ATM Project | 3 | ATM_1-3 | 292970 | Bug |  |  | 63929 | ATM 1.0 | MFT: Withdrawal Transaction Bug Test 14 | Function being tested: Withdrawal from checking account Initial State of the System: System is displaying the menu of withdrawal amounts Steps to reproduce the defect: 1. Choose an amount that the system currently has and which is not greater than the account balance Expected outcome: The ATM would output $60 to the user Actual outcome: The ATM output $100 to the user | 3 | Resolved | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 24, 2022 22:32 |  | 319982 | Adam Abouelhassan | Jan. 25, 2022 22:03 | 0 | 0
3646200 | 68407 | ATM Project | 4 | ATM_1-4 | 292970 | Bug |  |  | 63929 | ATM 1.0 | MFT: Withdrawal Bug Test 16 | Function being tested: System verifies that customer's balance is sufficient to fulfill the request Initial State of the System: System is requesting a withdrawal amount Steps to reproduce the defect: System is requesting a withdrawal amount 1. Choose an amount that the system currently has but which is greater than the account balance Expected outcome: The ATM would tell the user that the amount selected is greater than account balance Actual outcome: The ATM system went through with the transaction but instead of outputting the $200 requested, it output $20 to the user | 3 | Resolved | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 24, 2022 23:07 |  | 319982 | Adam Abouelhassan | Jan. 25, 2022 22:03 | 0 | 0
3649387 | 68407 | ATM Project | 8 | ATM_1-8 | 292970 | Bug |  |  | 63929 | ATM 1.0 | Typo #1 | Typo when asking user if they would like to do another transaction | 3 | Resolved | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 25, 2022 20:14 |  | 319982 | Adam Abouelhassan | Jan. 25, 2022 22:02 | 0 | 0
3645946 | 68407 | ATM Project | 2 | ATM_1-2 | 292970 | Bug |  |  | 63929 | ATM 1.0 | Withdrawal Bug | Function being tested: Withdrawal from savings account Initial State of the System: System is on and serving a customer Steps to reproduce the defect: 1. Insert card to machine 2. Enter card number 3. Enter PIN 4. Select #1 on the keypad for Withdrawal 5. Select #2 on the keypad for Savings 6. Select #5 on the keypad for $200 Expected outcome: The ATM would tell the user that their is insufficient cash available as there is only one $20 bill in the machine Actual outcome: The ATM system went through with the transaction but instead of withdrawing the $200 requested, it withdrew $20 which was option #1 (Pressing #1 on the keypad would tell the user that there is insufficient cash when this is not true) | 3 | Resolved | 3 | Normal | [6 empty] | 319979 | LAB1-35 | Jan. 24, 2022 21:41 |  | 319982 | Adam Abouelhassan | Jan. 25, 2022 22:02 | 0 | 0
3646265 | 68407 | ATM Project | 6 | ATM_1-6 | 292970 | Bug |  |  | 63929 | ATM 1.0 | MFT: Transfer Bug Test 29 | Function being tested: System performs a legitimate transfer transaction properly Initial State of the System: System is displaying a request for the customer to type a dollar amount Steps to reproduce the defect: 1. Enter a legitimate dollar amount Expected outcome: Funds should transfer from Checking to Savings Actual outcome: The ATM transfers an incorrect amount from Checking to Savings, $0.50 less than desired in this case | 2 | In Progress | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 24, 2022 23:26 |  | 319982 | Adam Abouelhassan | Jan. 25, 2022 21:45 | 0 | 0 | Jan. 25, 2022 21:32 Adam Abouelhassan Defect still exists in version 1.1
3646219 | 68407 | ATM Project | 5 | ATM_1-5 | 292970 | Bug |  |  | 63929 | ATM 1.0 | MFT: Deposit Bug Test 22 | Function being tested: System performs a legitimate deposit transaction properly Initial State of the System: System is requesting that customer insert an envelope Steps to reproduce the defect: 1. Enter $40 on keypad 2. Click to enter envelope Expected outcome: User's total balance should be increased by $40 Actual outcome: User's total balance was increased by only $39.90 | 2 | In Progress | 3 | Normal | [6 empty] | 319982 | Adam Abouelhassan | Jan. 24, 2022 23:14 |  | 319983 | Jaxson Waterstreet | Jan. 25, 2022 21:45 | 0 | 0 | Jan. 25, 2022 21:30 Adam Abouelhassan Defect still exists in version 1.1